## Project Timeline
TR-11 Commissioning Timeline
Chart showing project activities with a scrollable timeline is in this cell.
| ENTER START DATE: | 2019-11-24
Id | ACTIVITY | START | END | NOTES
-13 | Commencement of Commissioning | 2019-11-25 | 2019-11-29 | Finalization and power up of hardware setup
-12 | Milestone 1 | 2019-11-25 | 2019-11-29 | Filling the database in PLC to match actual drum occupancy
-11 | Milestone 2 | 2019-12-02 | 2019-12-02 | Establishment of connection between PLC and PG
-10 | Milestone 3 | 2019-12-02 | 2019-12-02 | Verification of accessibilty to all components on profibus network
-9 | Milestone 4 | 2019-12-02 | 2019-12-02 | Consistency check of HMI status w.r.t the OFF system state
-8 | Milestone 5 | 2019-12-02 | 2019-12-02 | Parametrization of system via HMI and Configuration of IND570
-7 | Milestone 6 | 2019-12-02 | 2019-12-02 | Configuration and Commissioning of all the DC drives
-6 | Milestone 7 | 2019-12-02 | 2019-12-03 | Temporary assignment of commissioning parameters of the system for easy operation
-5 | Milestone 8 | 2019-12-04 | 2019-12-04 | Test/Manual run of all three mechanisms with careful monitoring for speed and direction detection of motors
-4 | Milestone 9 | 2019-12-04 | 2019-12-04 | Ensuring validity of weight sensor via IND570
-3 | Milestone 10 | 2019-12-04 | 2019-12-04 | Calibration of position encoders
-2 | Milestone 11 | 2019-12-04 | 2019-12-04 | Acquisition of position data for distribution of areas
-1 | Milestone 12 | 2019-12-04 | 2019-12-05 | Configuration of weight parameters for safe hoist operation
0 | Milestone 13 | 2019-12-04 | 2019-12-05 | Fine tuning PID parameters and necessary changes in HMI program to match the new position values
1 | Milestone 14 | 2019-12-05 | 2019-12-06 | Verification of system protections and interlocks
2 | Milestone 15 | 2019-12-06 | 2019-12-06 | Performance of a complete crane operation in all modes using dummy load
3 | Milestone 16 | 2019-12-06 | 2019-12-07 | Making necessary amendments in the system to meet the requirements
4 | Final Milestone | 2019-12-07 | 2019-12-07 | Training and handing over the system to operator
Formulas:
END = Activities[[#This Row],[START]]+4
END = Activities[[#This Row],[START]]
Note on F6: 1. Since more places are occupied by the in the building, set complete database to 1 2. To enter vacant layers in the database, select all the adjacent entries of the layer and set them to 0 3. Now individually set the database locations to 0 corresponding to vacant positions in the building and use selection of multiple adjacent entries where applicable
Note on F7: - Use profinet bus for connection to PLC - On PG, set interface to auto CP577 in PG/PC interface settings if profibus protocol not working - If connecting through ethernet cable, make sure to assign proper addresses and changie the PG/PC interface settings - Try restarting the PG if connection cannot be established. Thoroughly check the interface settings for both PG and PLC for any abnormality
Note on F8: - In case of inaccessibility, check profibus cable for any faulty connections and position of terminating resistors - In remote IO module, connectivity of any single module affects accessibility of all the modules - Non-consistent hardware configurations also lead to inacessibility of modules - Make sure that the addresses of the hardware set via switches match the addresses set in the software project
Note on F9: 1. There are active no warnings and faults on alarm window 2. Drive state is ready with breaks electrically coupled and hand operation wheel de-coupled at individual drive screens 3. Bypass mode key is at OFF position indicated at the main screen 4. Emergency stop is released indicated at main screen 5. Weight, position and speed data is valid 6. Visual positions of bridge, trolley and hoist match on main screen match the actual position in field 7. No mode and mechanism is selected 8. The status at IO screens are consistent with the above mentioned indications
Note on F10: - Insert speed values, jog distance and the allowed setpoint deadband in the screen "Operation Parameters" - Perform load free calibration of load terminal using CalFree mode which requires setting the analog jumper gain (mV/V) and rated load cell capacity
Note on F11: - Configuration of incremental encoders - Soft shorting of IOs for brakes and fan control - Simulating an external input as 1 for motor ON control (requires 2 external signals to run) - Configuration of P2P connection for bridge motors and speed limit amendment for bridge motor 2 - Optimization runs for all the motors
Note on F12: Using dimensions from drawings and building layout: - Calibrate all absolute value encoders and soft limits of hoist, bridge and trolley - Enter all the zone and wall parameters - Configure hoist weight parameters
Note on F13: - Manually bring all the mechanisms except hoist away from hard limits for test run - Run bridge manually to note the relative directions of bridge motors 1 and 2. Make the required changes to program - Test run the bridge while monitering the synchronized operation of motors and note the direction of motion and the speed sign - Test run the trolley mechanism to note the direction of motion and the speed sign - Bring the system in the empty part of Zone E or A so that the hoist can move freely to its limits - Manually move hoist away from end limits and test run it to note the direction of motion and the speed sign - Make necessary changes to make the direction of motion compatible with the modes of operation
Note on F14: - Open and close multiple tubes and note the readings at weight terminal - Weight should decrease as the tubes open and should increase as the tubes close

## calcs (hidden)
*** This sheet should remain hidden ***
|  | Today: | 2021-05-03
5
|  | # of rows | 18
#N/A
#N/A
#N/A
|  | Window Activities: | 18 | #N/A
|  |  | 9 | #N/A
|  |  | 0 | #N/A
#N/A
#N/A
#N/A
|  |  |  | -13 | -13
|  |  |  | -12 | -12
|  |  |  | -11 | -11
|  |  |  | -10 | -10
|  |  |  | -9 | -9
|  |  |  | -8 | -8
|  |  |  | -7 | -7
|  |  |  | -6 | -6
|  |  |  | -5 | -5
|  | Calc Window Start | 2019-11-24
|  | Offset | 0
|  | Start | 2019-11-24
|  | Window | 30
Position | Series | Activity Id | Activity | 2019-11-24 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24
11.3 | 1 | -13 | Commencement of Commissioning | #N/A | 11.3 | 11.3 | 11.3 | 11.3 | 11.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10.3 | 2 | -12 | Milestone 1 | #N/A | 10.3 | 10.3 | 10.3 | 10.3 | 10.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9.3 | 3 | -11 | Milestone 2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8.3 | 4 | -10 | Milestone 3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7.3 | 5 | -9 | Milestone 4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6.3 | 6 | -8 | Milestone 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
5.3 | 7 | -7 | Milestone 6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
4.3 | 8 | -6 | Milestone 7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3 | 4.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3.3 | 9 | -5 | Milestone 8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2019-11-24 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23
|  | -13 | COMMENCEMENT OF COMMISSIONING | #N/A | #N/A | #N/A | #N/A | #N/A | 11.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -12 | MILESTONE 1 | #N/A | #N/A | #N/A | #N/A | #N/A | 10.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -11 | MILESTONE 2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -10 | MILESTONE 3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -9 | MILESTONE 4 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -8 | MILESTONE 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -7 | MILESTONE 6 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -6 | MILESTONE 7 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | -5 | MILESTONE 8 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2019-11-24 | 2019-11-25 | 2019-11-26 | 2019-11-27 | 2019-11-28 | 2019-11-29 | 2019-11-30 | 2019-12-01 | 2019-12-02 | 2019-12-03 | 2019-12-04 | 2019-12-05 | 2019-12-06 | 2019-12-07 | 2019-12-08 | 2019-12-09 | 2019-12-10 | 2019-12-11 | 2019-12-12 | 2019-12-13 | 2019-12-14 | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23
|  |  | Current Day | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2019-11-01 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | Nov 2019 - Top Band | 13 | 13 | 13 | 13 | 13 | 13 | 13 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2019-12-01 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  |  | Dec 2019 - Top Band | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
|  |  | 2019-11-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2019-12-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  |  | 3 | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON
|  |  |  | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
|  |  |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23